## Unified App Project - Technical
Unified App Project - Technical Solution Options Evaluation Matrix
Objective: To reduce total cost from Rabbit Rewards (RR) app and MyRabbit app through technical unification.
Instructions: Technical leads from both BUs (RR & MyRabbit) should review the options below, fill in estimated efforts, costs, impacts, and risks, and provide an initial architectural feasibility score (1-10: 1 Low -> 10 High ).
Option ID | Solution Option | Architectural Description | Implementation Effort (RR) | High Level Man-day (Dev) RR | Implementation Effort (MyRabbit) | High Level Man-day (Dev) MyRabbit | Propose | Integration Effort | Estimated Cost (Dev/Infra) | Risk | Pros(On technical RR side) | Cons(On technical RR side) | Pros(On technical MyRabbit side) | Cons(On technical MyRabbit side) | Technical & Business Impact | Risks & Limitations | Feasibility Score (1-10) | REMARKS /Limitation
1.1 | Webview: MyRabbit Main / RR Webview (Line Pay Container) | RR implements web features equivalent to app. Embedded into MyRabbit container webview. | 5 | 120 | 2 | 6-8 months | เก็บ | 8 |  | 5 | Leverages existing Next.js web codebase. (can handle by RD) Reduce application cost. | Webview limited device feature access (camera, geolocation). Noti & Deeplink CT Event track by MyRabbit app | note : same as rabbit connect - noti, deeplink handle by main app no pen test | Handle Noti & Deeplink from RR MyRabbit need to call CT SDK MyRabbit ไม่มี Huawei store | High limitations with webview format | UX/UI constraints; webview container limitations My Rabbit resource constrained until Jan'2027 change UX/UI, theme will impact more effort (+2 months at least) not include SSO merge effort |  | Quick win for proving integration concept. Main app name still be "MyRabbit" - change name need to process with bank ( at least +6 months) & recheck legal entity Myrabbit: scope fix SSO & noti & open web view RR: change all feature to web can move feature related to hardware to Myrabbit and call to RR
1.2 | Mini App Framework: UI + Backend inside Main Container | Develop mini-app framework. Needs container as main app to display. Run a small POC mini-app to test. | 5 | 180 |  |  | เก็บ | 8 |  | 8 | Each BU maintains UI independence. RR can focus on lifestyle features while MyRabbit handles financial. RR keeps full control over features and release cycle. Reusable mini-app framework benefits future integrations. | Requires restructuring ALL RR features into mini-app modules. No Flutter mini-app framework exists (must build from scratch). Container opensource / paid service - need owner | xxx | Topup - 8 Banking Pentest Container App MyRabbit ไม่มี Huawei store Pentest Container App มี session login คุม Bank regulation OS version ขั้นต่ำ, too large to implement | Low limitation features; each BU controls its own UI | Requires restructuring all features across both BUs My Rabbit resource constrained until Jan'2027 |  | Main container app need to call both mini app My rabbit: change to mini app, banking integrate RR: change to mini app integrate to main container app
1.3 | Mini App Hybrid: MyRabbit as Main Container / Other as Mini App | One app acts as the main host container that opens up to display the other app as a mini-app component. | 6 | 180 |  | force update depend on my rabbit, RR free to update 6-8 months | เก็บ | 8 |  | 5 | Each BU maintains UI independence. RR can focus on lifestyle features while MyRabbit handles financial. RR keeps full control over features and release cycle. Reusable mini-app framework benefits future integrations. | Requires restructuring ALL RR features into mini-app modules. No Flutter mini-app framework exists (must build from scratch). Deep link routing across apps is fragile. Auth token sharing between container/mini-app needs secure. | Main app follow security with BOT , Pentest security focus on My Rabbit, less on RR | Topup - 8 Banking Pentest Container App MyRabbit ไม่มี Huawei store Pentest Container App มี session login คุม Bank regulation OS version ขั้นต่ำ | Shared ecosystem; unified user base | Complex container management and app lifecycle alignment My Rabbit resource constrained until Jan'2027 change UX/UI, theme will impact more effort (+2 months at least) not include SSO merge effort |  | Use 3rd party as SDK container Main app name still be "MyRabbit" - change name need to process with bank ( at least +6 months) & recheck legal entity Myrabbit: scope fix SSO & noti & app container RR: change to mini app
1.4 | Mini App Hybrid: RR as Main Container / Other as Mini App | One app acts as the main host container that opens up to display the other app as a mini-app component. |  | 240 |  | 6-8 months | เก็บ | 10 |  | 10 |  | RR app develop by vendor |  | Noti & Deelink issue, deeplink use time to change service |  | change UX/UI, theme will impact more effort (+2 months at least) not include SSO merge effort |  | Use 3rd party as SDK container RR: change app to container & SSO, noti - register with bank (+6 months) Myrabbit: change to mini app
2 | SDK Integration (Feature Only) - Separate App | Both standalone apps remain. Specific features packaged into an SDK to be embedded into the container app. | 7 | 180 (Only SDK) |  |  | ตัด | 8 |  | 7 | Both apps stay independent — zero disruption to existing users. Feature sharing via SDK is modular. RR can control which features to expose. | Not true unification — both apps remain separate. SDK solves code sharing but not user experience merge or infra cost reduction. High ongoing maintenance cost from version fragmentation. | xxx | My rabbit sdk need to craet and support in long life support, and must follow to My Rabbit security along with my rabbit, Main app need to follow to BOT and pentest too. | Both apps remain independent; feature sharing via code dependency | High maintenance of SDK versions across both apps My Rabbit resource constrained until Jan'2027
3 | MyRabbit as Main App (Financial App Focus) | MyRabbit acts as main app. RR prefers API-based as it fits current features. SDK needs higher effort to enhance API (without UI). | 5 | 90 (API) |  |  | เก็บ | 5 |  | 3 | RR focuses on API-only integration. API - RR release independent (if app not update) | SDK - RR release cycle blocked by MyRabbit timeline. Loses direct user relationship. |  | My rabbit should handle UI for RR SDK, SDK need to update follow to sdk update, if using API update less than sdk | Financial-first UX; smooth payment integration | Release cycle is completely dependent on MyRabbit timeline My Rabbit resource constrained until Jan'2027
4 | Rabbit Rewards (RR) as Main App (Lifestyle App Focus) | Rabbit Rewards acts as main app, incorporating MyRabbit's financial features. | 9 | 180 |  |  | เก็บ | 5 |  | 5 | Full control over roadmap and release cycle. Existing RR features become central. No dependency on MyRabbit timeline. | Highest effort. Must absorb MyRabbit financial features (BOT compliance, KYC, payment gateway integration). RR codebase not designed for financial-grade security. | xxx | My rabbit need to wrap all api for RR,take time to implement | Lifestyle/rewards-first UX; drives daily engagement | High risk of regulatory non-compliance or delays with Bank of Thailand (BOT) My Rabbit resource constrained until Jan'2027
5 | Myrabbit as main app (add features RR in) | gradually add rabbit rewards feature (Native) in until 100% fade away RR
https://docs.google.com/presentation/d/1_deaCVipmmjeLzUXdNUT2iKXsibWVCrEug96RuUxF0Y/edit?slide=id.p1#slide=id.p1
Note on S5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add Remark column
Note on P6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @pichans@rabbit.co.th - I update the ranking score to 1-10 instead so we can differentiate the option easier krub. @auttapongb@vgi.co.th @aphichatk@rabbit.co.th krub - please help Mean to add/update/adjust if the needed krub - I added Pros & Cons column - please help to fill-in krub. Assigned to auttapongb@vgi.co.th Reply: Noted krub , will do :) Reply: ผมว่าเพิ่ม Timeline Estimation เข้าไปด้วยน่าจะดีไหมครับน่าจะถูกถามแน่ๆ
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: fix typo: companion to container

## Effort Estimation
Work Breakdown Structure - as "1" Person Effort
No# | Task / Feature | Team | Phase | Option 1 (MD/Duration) |  | Option 1 | Option 2 | Option 3 | Option 4 | Option 5 | Dependencies & Notes | Risk
|  |  |  | Man Days | Duration | Man Days | Man Days | Man Days | Man Days | Man Days
A. MYRABBIT TEAM — Tasks & Estimates
| Mini-App Framework: Flutter SDK (Build/Adapt) | MyRabbit | Build | [7 empty] | Build mini-app framework — can reuse from Option 2 exploration | High
| Convert MyRabbit Features to Mini-App Modules | MyRabbit | Build | [7 empty] | Restructure MyRabbit features into mini-app format | High
| 8-Bank Topup Deeplink Reconfiguration | MyRabbit | Build | [7 empty] | Each bank updates deeplink to RR app package name | Critical
| BOT Notification: Architecture Change | MyRabbit | Build | [7 empty] | Notify BOT, compliance review | Critical
| Container SSO + Token Sharing (MR side) | MyRabbit | Build | [7 empty] | Token sharing between mini-app and RR container | Medium
MYRABBIT SUBTOTAL
B. RABBIT REWARDS TEAM — Tasks & Estimates
| RR Container App Architecture Design | Rabbit Rewards | Build | [7 empty] | Design RR as container app | High
| Container App: Mini-App Loader + Lifecycle | Rabbit Rewards | Build | [7 empty] | Container loads/manages MyRabbit mini-app | High
| Container SSO + Unified Auth | Rabbit Rewards | Build | [7 empty] | Unified login across container and mini-app | Medium
| Bank Registration: RR as Financial App (+6 months BOT) | Rabbit Rewards | Build | [7 empty] | RR must register with BOT as financial app — 6-month regulatory process | Critical
| 8-Bank Topup Deeplink (RR side coordination) | Rabbit Rewards | Build | [7 empty] | Coordinate with banks for new package name | High
| Notification Management (RR container) | Rabbit Rewards | Build | [7 empty] | RR handles notification routing | Medium
| Pentest: RR Container App (first time) | Rabbit Rewards | Build | [7 empty] | RR first-ever pentest — significant effort | Critical
| KYC / Face Scan / PIN Integration (in RR) | Rabbit Rewards | Build | [7 empty] | MyRabbit mini-app handles these — RR just displays. Review only. | Low
| Campaign Service Bridge | Rabbit Rewards | Build | [7 empty] | Campaign service integration in container | Low
| RR UI/UX: Container Design System | Rabbit Rewards | Build | [7 empty] | Design system for container + mini-app feel | Medium
RABBIT REWARDS SUBTOTAL
C. TESTING & RELEASE PHASES
| PVT — RR Container App | QA/DevOps | Test | [7 empty] | Container private verification | High
| PVT — MyRabbit Mini-App | QA/DevOps | Test | [7 empty] | Mini-app private verification | Medium
| UAT — Combined (RR Container + MR Mini-App) | QA/DevOps | Test | [7 empty] | Joint UAT | High
| Pentest — MyRabbit Mini-App (re-cert) | QA/DevOps | Test | [7 empty] | Major BOT regulatory review for RR | Critical
| BOT Pre-Prod Review (RR as financial app) | QA/DevOps | Test | [7 empty] | First-time RR pentest | Critical
| Pentest — MyRabbit Mini-App (re-cert) | QA/DevOps | Test | [7 empty] | Re-certification | High
| 8-Bank UAT (Topup Deeplink with RR package) | QA/DevOps | Test | [7 empty] | All banks retest | Critical
| Production Release (RR container → MR mini-app enable) | QA/DevOps | Test | [7 empty] | Phased rollout | High
TESTING SUBTOTAL
GRAND TOTAL — Option 3: RR as Container + MyRabbit as Mini App | [7 empty] | 267

## Cost Estimation
Cost Estimation
WBS | Task / Feature | Phase | Option 1 (MD/Duration) |  | Option 1 | Option 2 | Option 3 | Option 4 | Option 5 | Dependencies & Notes | Risk
|  |  | Man Days | Duration
A. MYRABBIT TEAM
| Mini-App Framework: Flutter SDK (Build/Adapt) | Build |  |  |  | 222500 | 175000 | 175000 | 132000 | Build mini-app framework | High
| Convert MyRabbit to Mini-App / Web-Compatible | Build |  |  | 34500 | 184000 | 166500 | 143000 | 95000 | Restructure MR features | High
| 8-Bank Topup Deeplink Reconfiguration | Build |  |  |  | 95000 | 95000 | 95000 | 77500 | Each bank updates deeplink | Critical
| BOT Notification: Architecture Change | Build |  |  | 23500 | 64000 | 64000 | 64000 | 40500 | Notify BOT, compliance review | Critical
| Container SSO + Token Sharing (MR side) | Build |  |  | 47500 | 77500 | 54000 | 41000 | 47500 | Token sharing mini-app↔container | Medium
| Webview Container / Deeplink / CT SDK Setup | Build |  |  | 92500 |  |  |  | 34500 | Webview, deeplink routing, CT tracking | Low
| Pentest & Regression (MR side) | Build |  |  | 43000 | 95500 | 58500 | 37000 | 49500 | Pentest prep + feature regression | High
MYRABBIT SUBTOTAL |  |  |  |  | 241000 | 738500 | 613000 | 555000 | 476500
B. RABBIT REWARDS TEAM
| Convert ALL RR Features to Web / Mini-App Modules | Build |  |  | 302500 | 264000 | 242000 | 216500 | 175000 | All features to web or mini-app format | High
| RR Container App Architecture Design | Build | [5 empty] | 73000 |  | Design RR as container app | High
| Container: Mini-App Loader + Lifecycle | Build | [5 empty] | 103500 |  | Container loads/manages mini-app | High
| Container SSO + Unified Auth | Build |  |  | 71500 | 47500 | 41000 | 54000 | 47500 | Unified login across container+mini-app | Medium
| Bank Registration: RR as Financial App (+6mo BOT) | Build | [5 empty] | 63500 |  | RR must register with BOT | Critical
| 8-Bank Topup Deeplink (RR side) | Build |  |  | 34500 | 47500 | 41000 | 40500 | 47500 | Coordinate banks for new package name | High
| Notification / Campaign / SDK Bridge | Build |  |  | 138000 | 105500 | 105500 | 95000 | 142500 | Noti routing, campaign, SDK/API layer | Medium
| Pentest: RR Container App (first time) | Build |  |  |  | 37000 | 93000 | 65000 | 32500 | RR first-ever pentest | Critical
| RR UI/UX: Container Design System | Build |  |  | 90500 | 47500 | 47500 | 77500 | 47500 | Design system for container feel | Medium
| KYC/Face Scan/PIN + Privacy/Terms | Build |  |  | 17000 |  | 12000 | 12000 |  | MR mini-app handles — RR display only | Low
| End-to-End Regression + Perf Optimization | Build |  |  | 51500 | 95500 | 54000 | 63000 | 34500 | Full regression of all features | High
RABBIT REWARDS SUBTOTAL |  |  |  |  | 705500 | 644500 | 636000 | 863500 | 527000
C. TESTING & RELEASE PHASES
| PVT — Private Verification (per component) | Test |  |  | 48000 | 87000 | 72000 | 58500 | 45000 | Internal verification | High
| UAT — Combined Acceptance Test | Test |  |  | 48000 | 63000 | 54000 | 54000 | 39000 | Joint UAT, both teams+business | High
| BOT Pre-Prod Review & Compliance | Test |  |  | 29500 | 40000 | 40000 | 57000 | 23000 | BOT regulatory review | Critical
| Pentest — External + Internal Coord | Test |  |  | 41500 | 104500 | 89000 | 74000 | 43000 | Full pentest coordination | Critical
| 8-Bank UAT (Topup Deeplink) | Test |  |  |  | 67000 | 67000 | 67000 | 36500 | All banks retest deeplink | Critical
| Production Release (Phased Rollout) | Test |  |  | 27500 | 61500 | 49000 | 61500 | 44500 | Multi-phase rollout | High
TESTING SUBTOTAL |  |  |  |  | 194500 | 423000 | 371000 | 372000 | 231000
D. ADDITIONAL COSTS (Non-Man-Day)
| External Pentest Vendor |  |  |  | 350000 | 1950000 | 1950000 | 1150000 | 550000 | Full=฿800K, re-cert=฿350K
| 8-Bank Deeplink Coord (8×฿100K) |  |  |  |  | 800000 | 800000 | 800000 | 400000 | Legal+tech per bank
| BOT Registration / Filing |  |  |  | 50000 | 200000 | 200000 | 200000 | 50000 | BOT fee + legal
| Cloud Infrastructure (project period) |  |  |  | 300000 | 1200000 | 1200000 | 1200000 | 900000 | Minimal for 1.1; container for others
| Staging Env for BOT Review | [6 empty] | 400000 |  | Only for RR-as-financial options
| Mini-App 3rd Party SDK License (est.) |  |  |  |  | 500000 | 500000 | 500000 |  | If using commercial SDK
| Production Release Coordination |  |  |  | 200000 | 300000 | 300000 | 300000 | 300000 | App store + phased rollout
| Legal: App Name/Entity Change | [6 empty] | 150000 |  | If rebranding from MyRabbit
| SSO Merge (separate project — ALL options need) | [8 empty] | ~฿2,500,000. Excluded. Add if in scope.
| UX/Theme Rebrand (if unified branding required) | [8 empty] | +฿1,500,000 / +2 months. Excluded.
ADDITIONAL COSTS SUBTOTAL |  |  |  |  | 900000 | 4950000 | 4950000 | 4700000 | 2200000
GRAND TOTAL (Year 1) |  |  |  |  | 2041000 | 6756000 | 6570000 | 6490500 | 3434500
3-YEAR TCO |  |  |  |  | 9141000 | 20956000 | 20770000 | 20690500 | 14434500
⚠️ SSO Merge (~฿2.5M) REQUIRED for ALL options — excluded above.
⚠️ Option 1.4 (RR Container) needs +6 month BOT registration. Start BOT conversation NOW.
⚠️ MyRabbit team FROZEN until Jan 2027. Option 1.1 lowest MR impact.
⚠️ Bank deeplink (฿800K) is estimate. Survey all 8 banks before committing.
Rates: Dev ฿6,500/day, QA ฿4,500/day, PM ฿6,000/day — Thai fintech benchmarks.

## My Rabbit app concern
No. | topic | detail
1 | Topup deeplink |  | 6 month
Bank application specify package name to My rabbit app only with bank service code
most of Topup bank support with app 2 app deeplink
Deeplink callback to my rabbit with specific hostname that support to my rabbit only
Bank take time to change information around 4 month to update usage application form + retest+ UAT
Penetration test
My Rabbit has period to certify with Pentest in every year on every product that My rabbit integrate with, following to BOT standard
My rabbit access with low level feature that required to access device hardware
My Rabbit has process to CR before publish and required PVT on every change
Feature
My Rabbit has PIN
login only 1 device at once
device control
session control
face scan on transaction activity
face scan on log out
Virtual card implementation (need to update with NXP to control virtual card) minimum required for samsung feature (Android 16, OneUI8.5)
Notification
My Rabbit has own notification management
Campaign service
own campaign
Account
My rabbit based on phone verification and lock on with phone verify
My rabbit verify user to be owner with condition 1 user/ 1 account/ 1 citizen id/ 1 wallet
My Rabbit has own KYC process
User sharing? if unified app delete account? my rabbit will delete too?
System required
OS version (Android 9, iOs15.5) , Support OS following to BOT
No root, No jailbreak
No developer mode
No Accessibility Mode
No screen record
regulation
BOT approvement
GMS not support with huawei device

## Option 1 MyRabbit_container_Web (hidden)
WBS — Option 1: MyRabbit Main App + RR Webview
WBS | Task / Feature | Team | Phase | Dev (MD) | QA (MD) | PM/BA (MD) | Total MD | Dependencies & Notes | Risk
A. MYRABBIT TEAM — Tasks & Estimates
| SSO Integration (RR login via MyRabbit token) | MyRabbit | Build |  |  |  |  | Token sharing, session sync | Medium
| Webview Container Setup | MyRabbit | Build |  |  |  |  | Open webview from MyRabbit nav | Low
| Notification Bridge (RR → MyRabbit) | MyRabbit | Build |  |  |  |  | Handle noti routing from RR webview | Medium
| Deeplink Handling (RR pages via deeplink) | MyRabbit | Build |  |  |  |  | Route deeplinks to correct webview | Low
| CT Event Tracking SDK Integration | MyRabbit | Build |  |  |  |  | MyRabbit calls CT SDK for RR analytics | Low
| SSO + Token Security Review | MyRabbit | Build |  |  |  |  | Security audit for cross-app auth | Medium
| Regression Test (existing MyRabbit features) | MyRabbit | Build |  |  |  |  | Ensure existing features intact | Low
MYRABBIT SUBTOTAL
B. RABBIT REWARDS TEAM — Tasks & Estimates
1 | Convert ALL RR Features to Responsive Web | Rabbit Rewards | Build |  |  |  |  | Home, earn, burn, profile, history, campaign — all to Next.js web | High
2 | Webview Camera/Geolocation API | Rabbit Rewards | Build |  |  |  |  | Limited device access — shim for webview | Medium
3 | Notification via MyRabbit Bridge (API) | Rabbit Rewards | Build |  |  |  |  | API calls to MyRabbit noti service | Low
| Webview Deeplink Configuration | Rabbit Rewards | Build |  |  |  |  | Configure all deeplink routes for web | Low
| Campaign Service Integration (web) | Rabbit Rewards | Build |  |  |  |  | Campaign rendering in webview | Low
| RR Web UI/UX Redesign for In-App Feel | Rabbit Rewards | Build |  |  |  |  | Make web feel native (loading states, transitions) | Medium
| Privacy Policy & Terms Update | Rabbit Rewards | Build |  |  |  |  | Update legal for webview mode | Low
| End-to-End Regression Test (RR web) | Rabbit Rewards | Build |  |  |  |  | Full regression of all RR features as web | High
| Profile and Account Management | Rabbit Rewards | Build |  |  |  |  | Dashboard, Personal Info, Wallet, Card (display), Favorites, Points History, Help Center, Delete Account - all new web pages
| Notification System + News/Articles | Rabbit Rewards | Build |  |  |  |  | Notification list (filtered), detail, news/articles, inbox UI. Push via MyRabbit bridge API
| Lucky Draw | Rabbit Rewards | Build |  |  |  |  | Main draw page with wheel/game UI, group detail, history.
| Survey and Onboarding Flow | Rabbit Rewards | Build |  |  |  |  | Survey list+form, consent/opt-in, onboarding intro, data enrichment, add card (manual entry)
| Partner Clubs and Exclusive Stores | Rabbit Rewards | Build |  |  |  |  | Club page, exclusive store with nested tabs, bind/join flow, terms pages
| Scan and Earn (Web Part) + Subscription Enhancement | Rabbit Rewards | Build |  |  |  |  | Scan info page, manual code entry (no camera), history. Subscription detail, bundle, standalone pages
| Redemption | Rabbit Rewards | Build
RABBIT REWARDS SUBTOTAL
C. TESTING & RELEASE PHASES
| PVT — Private Verification Test (MyRabbit) | QA/DevOps | Test | 0 | 3 | 1 | 4 | Internal PVT on MyRabbit side | Low
| PVT — Private Verification Test (RR Web) | QA/DevOps | Test | 0 | 5 | 1 | 6 | Internal PVT on RR side | Low
| UAT — User Acceptance Test (Combined) | QA/DevOps | Test | 0 | 8 | 2 | 10 | Joint UAT with both teams + business | Medium
| BOT Pre-Prod Review | QA/DevOps | Test | 2 | 1 | 2 | 5 | If MyRabbit changes impact BOT scope | High
| Pentest (MyRabbit — annual cycle) | QA/DevOps | Test | 2 | 5 | 1 | 8 | Standard annual pentest | Medium
| Production Release (Phased: MyRabbit first, RR web enable) | QA/DevOps | Test | 1 | 2 | 2 | 5 | Phased rollout | Medium
TESTING SUBTOTAL | [6 empty] | 38
GRAND TOTAL — Option 1: MyRabbit Main App + RR Webview | [6 empty] | 191

## Option2 MyRabbit_container_SDK (hidden)
WBS — Option 2: Mini App Framework (Both in Container)
WBS | Task / Feature | Team | Phase | Dev (MD) | QA (MD) | PM/BA (MD) | Total MD | Dependencies & Notes | Risk
A. MYRABBIT TEAM — Tasks & Estimates
| Container App Architecture Design | MyRabbit | Build |  |  |  |  | Design how container loads mini-apps | High
| Mini-App Framework: Flutter SDK (Build) | MyRabbit | Build |  |  |  |  | Build from scratch — no Flutter mini-app framework exists | Critical
| Convert MyRabbit to Mini-App Modules | MyRabbit | Build |  |  |  |  | Restructure ALL MyRabbit features into mini-app format | High
| 8-Bank Topup Deeplink Reconfiguration | MyRabbit | Build |  |  |  |  | Each bank needs deeplink update (4 months each bank) | Critical
| BOT Notification & Compliance Update | MyRabbit | Build |  |  |  |  | Notify BOT of architectural change, compliance review | Critical
| Container SSO + Session Management | MyRabbit | Build |  |  |  |  | Unified auth across container and mini-apps | High
| Pentest: Container App | MyRabbit | Build |  |  |  |  | New container requires full pentest | Critical
| Pentest: MyRabbit Mini-App | MyRabbit | Build |  |  |  |  | MyRabbit mini-app pentest re-certification | High
| OS Version & Huawei Constraint Review | MyRabbit | Build |  |  |  |  | Verify mini-app framework on target OS versions | Medium
MYRABBIT SUBTOTAL
B. RABBIT REWARDS TEAM - Tasks and Estimates
| Convert ALL RR Features to Mini-App Modules | Rabbit Rewards | Build |  |  |  |  | Restructure every RR feature into mini-app format | High
| Mini-App Lifecycle + Navigation | Rabbit Rewards | Build |  |  |  |  | Mini-app lifecycle management (load, unload, state) | Medium
| RR SDK/API Layer for Container Communication | Rabbit Rewards | Build |  |  |  |  | API layer for container ↔ mini-app communication | Medium
| Campaign Service in Mini-App | Rabbit Rewards | Build |  |  |  |  | Campaign rendering in mini-app | Low
| RR Mini-App Pentest Preparation | Rabbit Rewards | Build |  |  |  |  | Prepare RR mini-app for security review | Medium
| Mini-App Performance Optimization | Rabbit Rewards | Build |  |  |  |  | Ensure smooth loading, memory management | Medium
| End-to-End Regression (all modules) | Rabbit Rewards | Build |  |  |  |  | Full regression of all RR features as mini-app | High
OPT2.B.8 | [6 empty] | 17 | Full regression of all RR features as mini-app in container | High
RABBIT REWARDS SUBTOTAL |  |  |  | 145 | 61 | 30 | 236
C. TESTING & RELEASE PHASES
| PVT — Container App (Internal) | QA/DevOps | Test |  |  |  |  | Container app internal verification | High
| PVT — MyRabbit Mini-App | QA/DevOps | Test |  |  |  |  | Mini-app internal verification | Medium
| PVT — RR Mini-App | QA/DevOps | Test |  |  |  |  | Mini-app internal verification | Medium
| UAT — Combined (Container + Both Mini-Apps) | QA/DevOps | Test |  |  |  |  | Full joint UAT | High
| BOT Pre-Prod Review (MyRabbit) | QA/DevOps | Test |  |  |  |  | BOT regulatory review | Critical
| Pentest — Container + Both Mini-Apps | QA/DevOps | Test |  |  |  |  | Full pentest: container, MR mini-app, RR mini-app | Critical
| 8-Bank UAT (Topup Deeplink) | QA/DevOps | Test |  |  |  |  | Each bank retests deeplink with new package | Critical
| Production Release (Phased: container → MR mini → RR mini) | QA/DevOps | Test |  |  |  |  | Multi-phase production rollout | High
TESTING SUBTOTAL
GRAND TOTAL - Option 2: Mini App Framework (Both in Container) | [6 empty] | 236 | RR Build (236) + Testing + MyRabbit (estimates needed from other teams) | High